## Sheet1
Days | Team Members | Day Wise Task Assigned | Status of Completion
Day 1 (13/08/2018) | S.Swaroopa | User Stories and partial involment in pages creation | Completed
| K. Ashritha | CapStore Home Page front end | Static Page Partially Created
| M.Sindhu | Wish List Page Front End | Static Page Partially Completed
| I.P.S.Prakash | Product Page front end | Static Page Partially Completed
Day 2 (14/08/2018) | S.Swaroopa | Product Page (Modifications) | Partially Completed
| K. Ashritha | CapStore Home Page front end | static page Completed
| M.Sindhu | Wish List Page front end | static page Completed
| I.P.S.Prakash | Product Page Front End | static page Completed
Day 3 (16/08/2018) | S.Swaroopa | Wish List Rest Api Creation | Partially Completed
| K. Ashritha | CapStore Home Page | Completed static page and linked with other pages
| I.P.S.Prakash | Product Page front end | Completed linking with other frontend pages
| M.Sindhu | Wish List Page Front End | Completed linking with other frontend pages
Day 4 (17/08/2018) | S.Swaroopa | Wish List dummy Data | fetching Details Completed
| K. Ashritha | CapStore Home Page Rest Api | fetching Details Completed
| I.P.S.Prakash | Similar Products,Feed Back Front End | Completed
| M.Sindhu | Wish Lsit Dummy Data | fetching Details Completed