## Sheet1
Days | Team Members | Day Wise Task Assigned | Status of Completion
Day 1 (13/08/2018) | Shivani Katolkar | Home page designing for merchant. | Completed
| Deepanshu Joshi | Common Header Footer for Website Designed. | Completed
| R Vignesh | Home page designing for admin. | Completed
| Kavya S V | Home page designing for customer. | Completed
Day 2 (14/08/2018) | Shivani Katolkar | Merchant page designing(add,remove,update pages,etc) | Completed
| Deepanshu Joshi | Login for website and sign up. | Login completed, sign up pending.
| R Vignesh | Admin page designing. | Completed
| Kavya S V | Customer page designing. | Completed
Day 3 (16/08/2018) | Shivani Katolkar | Merchant page designing(modifications). | Completed
| Deepanshu Joshi | Login & sign up. | Completed
| R Vignesh | Admin page designing(modifications). | Completed
| Kavya S V | Customer page designing(modifications). | Completed
Day 4 (17/08/2018) | Shivani Katolkar | Final Front End Merchant page and back end for profile. | Back end for profile pending.
| Deepanshu Joshi | Final Front End Login page and back end. | Back end pending.
| R Vignesh | Final Front End Admin page and back end. | Back end pending.
| Kavya S V | Order page added & back end for edit profile. | Back end for edit profile pending.