## Sheet1
Days | Team Members | Day wise task assigned | Status of completion
Day-1 | Shubhendu | user stories | Completed
| Praneetha | page designing | In progress
| Shravya | user stories | Completed
| Shafeeq | user stories | Completed
Day-2 | Shubhendu | created POJO classes | completed
| Praneetha | Shipping adress Page designing | Completed
| Shravya | Queries creation | Completed
| Shafeeq | Controller functionality | In progress
Day-3 | Shubhendu | back end | In progress
| Praneetha | back end | In progress
| Shravya | back end | In progress
| Shafeeq | back end | In progress
Day-4 | Shubhendu | Rest API | In progress
| Praneetha | Rest API | In progress
| Shravya | Rest API | In progress
| Shafeeq | Rest API | In progress